## ProjectSchedule
CampusConnect — Closed-Community Academic & Social Platform
Aayushmaan Singh Meyan (1024240142) |  | Project Start: | 2026-08-17
Divyansh Jasrotia (1024240008) |  | Today: | 2026-09-06
Prakhar Saxena (1024240019) |  | Display Week: | 1
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS
Phase 0 — Project Scaffold
Task 0.1 — Initialize Next.js Project | Aayushmaan Singh Meyan | 100% | 2026-08-17 | 2026-08-18
Task 0.2 — Install Core Dependencies | Aayushmaan Singh Meyan | 100% | 2026-08-18 | 2026-08-20
Task 0.3 — Initialize Prisma & Provider Config | Aayushmaan Singh Meyan | 100% | 2026-08-20 | 2026-08-22
Task 0.4 — Create .env.example Environment Spec | Aayushmaan Singh Meyan | 100% | 2026-08-22 | 2026-08-23
Task 0.5 — Update Build & Dev Makefile in code/ | Aayushmaan Singh Meyan | 100% | 2026-08-24 | 2026-08-25
Task 0.6 — Configure next.config.ts (Remote Images) | Aayushmaan Singh Meyan | 100% | 2026-08-25 | 2026-08-26
Task 0.7 — Configure Global Styles (globals.css) | Aayushmaan Singh Meyan | 100% | 2026-08-26 | 2026-08-28
Phase 1 — Database Schema (Prisma)
Task 1.1 — Define Prisma Schema (14 Models & Enums) | Aayushmaan Singh Meyan | 100% | 2026-08-28 | 2026-08-30
Task 1.2 — Run Initial Migration & Generate Client | Aayushmaan Singh Meyan | 100% | 2026-08-30 | 2026-08-31
Task 1.3 — Create Seed File (prisma/seed.ts) | Aayushmaan Singh Meyan | 100% | 2026-08-31 | 2026-09-01
Phase 2 — Core Library Setup
Task 2.1 — Prisma Client Singleton (src/lib/prisma.ts) | Divyansh Jasrotia | 100% | 2026-09-01 | 2026-09-02
Task 2.2 — NextAuth Configuration (src/lib/auth.ts) | Divyansh Jasrotia | 100% | 2026-09-01 | 2026-09-02
Task 2.3 — TypeScript Type Extensions (src/types/next-auth.d.ts) | Divyansh Jasrotia | 100% | 2026-09-02 | 2026-09-02
Task 2.4 — Cloudinary Helper (src/lib/cloudinary.ts) | Divyansh Jasrotia | 100% | 2026-09-02 | 2026-09-02
Task 2.5 — Gemini AI Helper (src/lib/gemini.ts) | Prakhar Saxena | 100% | 2026-09-03 | 2026-09-04
Task 2.6 — Utility Functions (src/lib/utils.ts) | Prakhar Saxena | 100% | 2026-09-04 | 2026-09-05
Task 2.7 — Socket.io Client Helper (src/lib/socket.ts) | Prakhar Saxena | 100% | 2026-09-05 | 2026-09-06
Task 2.8 — Route Guard Middleware (src/middleware.ts) | Prakhar Saxena | 100% | 2026-09-06 | 2026-09-06
Phase 3 — Deliverable 1: Authentication & User System
Task 3.1 — NextAuth API Route (src/app/api/auth/[...nextauth]/route.ts)
Task 3.2 — Register API (src/app/api/register/route.ts)
Task 3.3 — Auth Pages UI (Layout, Login, Register, Verify)
Task 3.4 — Session Provider Wrapper (src/app/layout.tsx)
Task 3.5 — Invite Link System (src/app/api/admin/invite/route.ts)
Phase 4 — Deliverable 2: User Profiles & Social Network
Task 4.1 — Dashboard Layout (src/app/(dashboard)/layout.tsx)
Task 4.2 — Profile Page & API (src/app/api/users/[id])
Task 4.3 — Friend System API & UI (src/app/api/friends)
Task 4.4 — Social Feed API & UI (src/app/api/posts)
Phase 5 — Deliverable 3: Academic Groups & Course Materials
Task 5.1 — Groups API (src/app/api/groups)
Task 5.2 — Group Pages UI (Grid, Feed, Members)
Task 5.3 — Course Materials API (src/app/api/groups/[id]/materials)
Task 5.4 — Course Materials UI (FileUploader & PdfViewerModal)
Phase 6 — Deliverable 4: Schedule Board
Task 6.1 — Events API (src/app/api/events)
Task 6.2 — Schedule UI (CalendarView & EventModal)
Task 6.3 — Event Notifications & Socket Broadcast
Phase 7 — Deliverable 5: Real-Time Communication
Task 7.1 — Custom Server Setup (server.ts with Socket.io)
Task 7.2 — Messaging API (src/app/api/messages)
Task 7.3 — Messaging UI (UserChatList & ChatBox)
Task 7.4 — Notifications API (src/app/api/notifications)
Task 7.5 — Notification Bell UI (NotificationDropdown.tsx)
Phase 8 — Deliverable 6: Admin Control Panel
Task 8.1 — Admin API Routes (Users, Settings, Reports)
Task 8.2 — Admin Pages (Dashboard, Users, Moderation, Settings)
Task 8.3 — Role Guards (Middleware & API Protection)
Phase 9 — Deliverable 7: AI Agentic Moderation
Task 9.1 — Moderation Flow in POST /api/posts
Task 9.2 — Sensitivity Levels (STRICT / MODERATE / LENIENT)
Task 9.3 — Admin AI Controls & Analytics
Phase 10 — Deliverable 8: Polish & Deployment
Task 10.1 — Responsive Design Audit (Mobile/Tablet/Desktop)
Task 10.2 — Loading States, Skeletons & Empty States
Task 10.3 — GitHub Actions CI (.github/workflows/ci.yml)
Task 10.4 — Production Cloud Deployment (Vercel + Neon DB)
Task 10.5 — Update Documentation (docs/index.md)
Task 10.6 — UAT Checklist & Role Verification
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.